## User-Stories
ID | Theme | As a/an | I want to | so that | Notes | Priority | Status | Tasks # | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 |  | Product Owner | Store all the customers information | it can be retrieved at any time |  |  | Waiting | 5
Create Database Model
Create a relational database
Validate data input
Ensure Primary keys are present
Ensure Foreign keys are present
2 |  | Administrator | Have all data in a relational databse | All related data will be aligned properly |  |  |  | 3
Enter all customer data
Enter prescription data
Enter Doctor Contact information
3 |  | User | A secure login connection | So my order is secured |  |  |  | 2
Create Login page
Verify password
4 |  | User | Use a form for data entry | so it is easier to fill in the required information |  |  |  | 2
[5 empty] | I think we can consolidate these three. |  |  |  | Create Customer Form for data input
Validate data input
5 |  | User | I want access to the database | I can save all data when ordering
6 |  | User | I want to add my own data | Use the system as a new user
7 |  | User | Edit my data | I can make changes as needed
8 |  | Administrator | I want all data validated | All data is accurate for orders and reports |  |  |  | 1
Create validation on Customer form for enetering data
9 |  | Pharmacist | Escalated login credentials | I can verify access to higher level functions and data |  |  |  | 3
Create database role for database Administrator
Create database role for Pharmacist
Create database role for Customer
10 |  | Pharmacist | A separate page from customer page | I can access reports and customer list |  |  |  | 2
Create reports
Create Queries
11 |  | User | View a complete list of my prescritions | so I can select which ones to refill |  |  |  | 2
Create autofill of needed data
Make a check list for customers to choose from
12 |  | Pharmacist | A full report of the days orders | I know how many prescriptions will be mailed |  |  |  | 2
Create reports
Create Queries
13 |  | User | Review my order prior to payment | So I can verify it is correct |  |  |  | 1
14 |  | User | My mailing address to autofill | So I do not have to enter it every time I order |  |  |  | 1
Autofill customers data when logged in
15 |  | Pharmacist | Doctors contact information included | I can request a prescription renewal when needed |  |  |  | 2
Create a table for primary doctors contact information
Create Primary/Foreign Keys
16 |  | User | View my order history | I can ensure it is accurate |  |  |  | 1
Create a pop up asking user to make sure data is correct before sending order
17 |  | User | A bug free experience | I am sure the application is working correctly |  |  |  | 1
Testing
[6 empty] | Total Tasks |  | 28

## Product Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2022-02-16 | 28 | 28
Thur | 2022-02-17 | 27
Fri | 2022-02-18 | 27
Sat | 2022-02-19 | 27
Sun | 2022-02-20 | 26
Mon | 2022-02-21 | 25
Tues | 2022-02-22 | 24
Wed | 2022-02-23 | 23
Thur | 2022-02-24 | 22
Fri | 2022-02-25 | 21
Sat | 2022-02-26 | 20
Sun | 2022-02-27 | 19
Mon | 2022-02-28 | 18
Tues | 2022-03-01 | 18
Wed | 2022-03-02 | 18
Thur | 2022-03-03 | 18
Fri | 2022-03-04 | 17
Sat | 2022-03-05 | 16
Sun | 2022-03-06 | 15
Mon | 2022-03-07 | 14
Tues | 2022-03-08 | 13
Wed | 2022-03-09 | 12
Thur | 2022-03-10 | 11
Fri | 2022-03-11 | 11
Sat | 2022-03-12 | 11
Sun | 2022-03-13 | 11
Mon | 2022-03-14 | 11
Tues | 2022-03-15 | 11
Wed | 2022-03-16 | 11
Thur | 2022-03-17 | 11
Fri | 2022-03-18 | 11
Sat | 2022-03-19 | 10
Sun | 2022-03-20 | 9
Mon | 2022-03-21 | 8
Tues | 2022-03-22 | 7
Wed | 2022-03-23 | 6
Thur | 2022-03-24 | 5
Fri | 2022-03-25 | 4
Sat | 2022-03-26 | 3
Sun | 2022-03-27 | 2
Mon | 2022-03-28 | 2
Tues | 2022-03-29 | 2
Wed | 2022-03-30 | 2
Thur | 2022-03-31 | 2
Fri | 2022-04-01 | 1
Sat | 2022-04-02 | 1
Sun | 2022-04-03 | 1
Mon | 2022-04-04 | 1
Tues | 2022-04-05 | 0

## Sprint 1 Planning
User Story | Tasks | Team Member | Hours Estimated | Actual Hours
As a Product Owner I want to store all customer data so it can be retrievd at any time | Create Database Model | Jim | 3
| Create a relational database | Jim | 6
| Validate data input | Jim | 1
| Ensure Primary keys are present | Jim | 1
| Ensure Forgein keys are present | Jim | 1
As an Administrator I want to have a ll data in a relational database so all data will be ailigned properly | Enter customer data | Jim | 2
| Enter prescription data | Jim | 2
| Enter doctor contact information | Jim | 2
As a User I want a secure Login connection so my order is secured | Create Login Page | AD/SP
| Verify Password | AD/SP
As a User I want a form for data entry so it is easier to fill in my data | Create Customer form for data entry | AD/SP
| Validate data input | AD/SP
|  | Total | 18 | 0
|  | Hours/member | 4.5

## Sprint 1 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2022-02-17 | 12 | 0
Thurs | 2022-02-18 | 11 | 0
Fri | 2022-02-19 | 10 | 0
Sat | 2022-02-20 | 9 | 0
Sun | 2022-02-21 | 8 | 0
Mon | 2022-02-22 | 7 | 0
Tues | 2022-02-23 | 6 | 0
Wed | 2022-02-24 | 5 | 0
Thurs | 2022-02-25 | 4 | 0
Fri | 2022-02-26 | 3 | 0
Sat | 2022-02-27 | 2 | 0
Sun | 2022-02-28 | 1 | 0
Mon | 2022-03-01 | 0 | 0
Tues | 2022-03-02 | 0 | 0
Mid-Sprint
Velocity: 5 tasks assigned and 3 completed. Should have the other 2 done by end of sprint.
Testing
3 tasks fully tested and passed.
Screenshots
Code