## User-Stories
ID | Theme | As a/an | I want to | so that | Notes | Priority | Status | Tasks # | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 |  | Product Owner | Store all the customers information | it can be retrieved at any time |  |  |  | 5
[7 empty] | Complete |  | Create Database Model
[7 empty] | Complete |  | Create a relational database
[7 empty] | Complete |  | Validate data input
[7 empty] | Complete |  | Ensure Primary keys are present
[7 empty] | Complete |  | Ensure Foreign keys are present
2 |  | Administrator | Have all data in a relational databse | All related data will be aligned properly |  |  |  | 3
[7 empty] | In-Progress |  | Enter all customer data
[7 empty] | In-Progress |  | Enter prescription data
[7 empty] | In-Progress |  | Enter Doctor Contact information
3 |  | User | A secure login connection | So my order is secured |  |  |  | 3
[7 empty] | Complete |  | Create connection string for form to connect to database
[7 empty] | Complete |  | Create Login page
[7 empty] | Complete |  | Verify username and password
4 |  | User | Use a form for data entry | so it is easier to fill in the required information |  |  |  | 2
[7 empty] | Complete |  | Create Customer Form for data input
[7 empty] | Complete |  | Create textboxes for each data field
5 |  | User | I want access to the database | I can save all data when ordering |  |  |  | 2
[7 empty] | Complete |  | Create save function to insert user data
[7 empty] | Complete |  | Create save button in UI
6 |  | User | Edit my data | I can make changes as needed |  |  |  | 2
[7 empty] | Complete |  | Create edit function to change existing data
[7 empty] | Complete |  | Create edit button in UI
7 |  | User | Log out when finished | my data is secured |  |  |  | 2
[7 empty] | Complete |  | Create Logout Function
[7 empty] | Complete |  | Create logout button in UI
19
8 |  | Administrator | I want all data validated | All data is accurate for orders and reports |  |  |  | 1
[7 empty] | Waiting |  | Create validation on Customer form for entering data
9 |  | Pharmacist | Escalated login credentials | I can verify access to higher level functions and data |  |  |  | 3
[7 empty] | Waiting |  | Create database role for database Administrator
[7 empty] | Waiting |  | Create database role for Pharmacist
[7 empty] | Waiting |  | Create database role for Customer
10 |  | Pharmacist | A separate page from customer page | I can access reports and customer list |  |  |  | 3
[7 empty] | Waiting |  | Create 3rd panel for Admin UI
[7 empty] | Waiting |  | Create reports
[7 empty] | Waiting |  | Create Queries
7
11 |  | User | View a complete list of my prescritions | so I can select which ones to refill |  |  |  | 2
[7 empty] | Waiting |  | Create autofill of needed data
[7 empty] | Waiting |  | Make a check list for customers to choose from
12 |  | Pharmacist | A full report of the days orders | I know how many prescriptions will be mailed |  |  |  | 2
[7 empty] | Waiting |  | Create reports
[7 empty] | Waiting |  | Create Queries
13 |  | User | Review my order prior to payment | So I can verify it is correct |  |  |  | 1
[7 empty] | Waiting |  | Create Pop-up for order verification
14 |  | User | My mailing address to autofill | So I do not have to enter it every time I order |  |  | Waiting | 1
[7 empty] | Waiting |  | Autofill customers data when logged in
15 |  | Pharmacist | Doctors contact information included | I can request a prescription renewal when needed |  |  |  | 2
[7 empty] | Waiting |  | Create a table for primary doctors contact information
[7 empty] | Waiting |  | Create Primary/Foreign Keys
16 |  | User | View my order history | I can ensure it is accurate |  |  |  | 1
[7 empty] | Waiting |  | Create a pop up asking user to make sure data is correct before sending order
9
17 |  | User | A bug free experience | I am sure the application is working correctly |  |  |  | 1
[7 empty] | Waiting |  | Testing
1
[6 empty] | Total Tasks |  | 36

## Product Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2022-02-16 | 36 | 36
Thur | 2022-02-17 | 29 | 33
Fri | 2022-02-18 | 29 | 31
Sat | 2022-02-19 | 29 | 30
Sun | 2022-02-20 | 28 | 26
Mon | 2022-02-21 | 27 | 25
Tues | 2022-02-22 | 26 | 25
Wed | 2022-02-23 | 26 | 24
Thur | 2022-02-24 | 24 | 24
Fri | 2022-02-25 | 21 | 22
Sat | 2022-02-26 | 20 | 20
Sun | 2022-02-27 | 19 | 18
Mon | 2022-02-28 | 18 | 17
Tues | 2022-03-01 | 18 | 16
Wed | 2022-03-02 | 18
Thur | 2022-03-03 | 18
Fri | 2022-03-04 | 17
Sat | 2022-03-05 | 16
Sun | 2022-03-06 | 15
Mon | 2022-03-07 | 14
Tues | 2022-03-08 | 13
Wed | 2022-03-09 | 12
Thur | 2022-03-10 | 11
Fri | 2022-03-11 | 11
Sat | 2022-03-12 | 11
Sun | 2022-03-13 | 11
Mon | 2022-03-14 | 11
Tues | 2022-03-15 | 11
Wed | 2022-03-16 | 11
Thur | 2022-03-17 | 11
Fri | 2022-03-18 | 11
Sat | 2022-03-19 | 10
Sun | 2022-03-20 | 9
Mon | 2022-03-21 | 8
Tues | 2022-03-22 | 7
Wed | 2022-03-23 | 6
Thur | 2022-03-24 | 5
Fri | 2022-03-25 | 4
Sat | 2022-03-26 | 3
Sun | 2022-03-27 | 2
Mon | 2022-03-28 | 2
Tues | 2022-03-29 | 2
Wed | 2022-03-30 | 2
Thur | 2022-03-31 | 2
Fri | 2022-04-01 | 1
Sat | 2022-04-02 | 1
Sun | 2022-04-03 | 1
Mon | 2022-04-04 | 1
Tues | 2022-04-05 | 0

## Sprint 1 Planning
User Story | Tasks | Team Member | Hours Estimated | Actual Hours
As a Product Owner I want to store all customer data so it can be retrievd at any time | Create Database Model | Jim | 1 | 2
| Create a relational database | Jim | 6 | 1
| Validate data input | Jim | 1 | 1
| Ensure Primary keys are present | Jim | 1 | 1
| Ensure Forgein keys are present | Jim | 1 | 1
As an Administrator I want to have a ll data in a relational database so all data will be ailigned properly | Enter customer data | Jim | 2 | 3
| Enter prescription data | Jim | 2 | 3
| Enter doctor contact information | Jim | 2 | 3
As a User I want a secure Login connection so my order is secured | Create connection string | Adrian | 1 | 2
| Create Login Page | Sara | 1 | 1
| Verify username and Password | Adrian | 2 | 1
As a User I want a form for data entry so it is easier to fill in my data | Create Customer form for data entry | Sara | 2 | 2
| Create textboxes for each data field | Sara | 1 | 1
As a User, I want to access the database, so that I can save all data when ordering | Create save function to insert user data | Adrian | 1 | 1
| Create save button in UI | Sara | 1 | 1
As a User, I want to edit my data, so I can make changes as needed | Create edit function to update data | Adrian | 1 | 2
| Create edit button in UI | Sara | 1 | 1
As a User, I want to log out when finished so that my data is secured | Create logout function | Adrian | 1 | 1
| Create logout button in UI | Adrian | 1 | 1
|  | Total | 29 | 29
|  | Hours/member | 9.67 | 9.67

## Sprint 1 Burndown
Time |  | Tasks | [5 empty] | Jim Planned | Jim Daily | Sara Planned | Sara Daily | Adrian Planned | Adrian Daily | Team Planned | Team Daily
Day | Date | Planned | Actual |  |  |  | Total
Wed | 2022-02-17 | 19 | 19 |  |  |  | Wed | 8 | 0 | 5 | 0 | 6 | 0 | 19 | 0
Thurs | 2022-02-18 | 19 | 16 |  |  |  | Thu | 8 | 0 | 5 | 2 | 6 | 1 | 19 | 3
Fri | 2022-02-19 | 16 | 14 |  |  |  | Fri | 8 | 2 | 3 | 0 | 5 | 0 | 16 | 2
Sat | 2022-02-20 | 14 | 13 |  |  |  | Sat | 6 | 1 | 3 | 0 | 5 | 0 | 14 | 1
Sun | 2022-02-21 | 13 | 9 |  |  |  | Sun | 5 | 2 | 3 | 1 | 5 | 1 | 13 | 4
Mon | 2022-02-22 | 9 | 8 |  |  |  | Mon | 3 | 0 | 2 | 0 | 4 | 1 | 9 | 1
Tues | 2022-02-23 | 8 | 8 |  |  |  | Tue | 3 | 0 | 2 | 0 | 3 | 0 | 8 | 0
Wed | 2022-02-24 | 8 | 8 |  |  |  | Wed | 3 | 0 | 2 | 0 | 3 | 0 | 8 | 0
Thurs | 2022-02-25 | 8 | 6 |  |  |  | Thu | 3 | 0 | 2 | 0 | 3 | 2 | 8 | 2
Fri | 2022-02-26 | 4 | 4 |  |  |  | Fri | 2 | 1 | 1 | 1 | 1 | 0 | 4 | 2
Sat | 2022-02-27 | 2 | 2 |  |  |  | Sat | 1 | 1 | 0 | 1 | 1 | 0 | 2 | 2
Sun | 2022-02-28 | 1 | 1 |  |  |  | Sun | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1
Mon | 2022-03-01 | 1 | 1 |  |  |  | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Tues | 2022-03-02 | 0 | 0 |  |  |  | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-Sprint
|  | Planned | Actual | TODO | %
Velocity: |  | 19 | 11 | 6 | 57.89% | The remaining 6 should be done before end of sprint.
Testing
3 tasks fully tested and passed.
Screenshots
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 1 Demo
Task | By | Accepted | Notes
Create Database Model | Jim | Yes
Create a relational database | Jim | Yes
Validate data input | Jim | Yes
Ensure Primary keys are present | Jim | Yes
Ensure Forgein keys are present | Jim | Yes
Enter customer data | Jim | Yes
Enter prescription data | Jim | Yes
Enter doctor contact information | Jim | Yes
Create connection string | Adrian | Yes
Create Login Page | Sara | Yes
Verify username and Password | Adrian | Yes
Create Customer form for data entry | Sara | Yes
Create textboxes for each data field | Sara | Yes
Create save function to insert user data | Adrian | Yes
Create save button in UI | Sara | Yes
Create edit function to update data | Adrian | Yes
Create edit button in UI | Sara | Yes
Create logout function | Adrian | Yes | Added after mid-sprint
Create logout button in UI | Adrian | Yes | Added after mid-sprint

## Sprint 1 Review
Done | Updated | Notes
2022-03-01 | Product backlog updated for new design concepts | None
| PO satisifed with demo and sprint 1 | None
Changes for next sprint |  |  |  |  | Remarks
1 | The DOB field has the time in it for some reason. I'm not sure if that's a C# issue or a SQL issue, but it looks silly and is causing some problems code-wise. |  |  |  | Changes will be made
2 | We need phone and email textboxes for panel 2 (general user panel). We have them in panel 3, but not 2. |  |  |  | Changes will be made
3 | The extra resources in the repo need to be deleted because they're causing conflicts when I pull from the repo. The form doesn't know which file to use sometimes. They are the form1.cs, form1.designer.cs, and form1.resx and were added when we were figuring out Sara's merge. I have all that in the code now, so no data will be lost |  |  |  | Deleted Screenshot
4 | We have 1 allergy field in the database, but three in the UI. I think we need to decide whether to add more to the database or have just one large text area for the allergy field in the UI |  |  |  | I used one large text field to list allergies. I thought that was easier than multiple
5 | We need to decide for sure how we're going to handle customer lookup. I know it's more work on the db, but I think the easiest option for cleaner code would be to have another column for username in Customers_List. Right now, just to test the code I have it so that I'm looking it up by customer ID, but that could get quite tedious keeping track of which IDs are administrative, etc. |  |  |  | I can add username. I am also thinking of combining name into one bx instead of separate boxes for first and last name. The reason for this is when searching for customer names, you just need to list one column instead of two as it is now
6 | Do you think we need a 4th panel for the customer refill options? Because I'm not quite sure how we're going to handle that at the moment. |  |  |  | can make a 4th panel, will it be easier for you adrian? logically, it could work. Customers would need to input their data first before submitting a refill request.
7 | Sara - if you get bored, you should mess around with the color scheme of the form to set it apart from generic forms. Not terribly important, but it makes it prettier to look at |  |  |  | if only I had the time to be bored xD but yes I will set some time on the side to look into color schemes and such.
End-Sprint
Sprint velocity consisted of 19 tasks assigned and 19 tasks completed. No adjustments needed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 19 | 19
Testing Strategy
All 19 tasks passed testing.
Screenshots
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 1 Retrosepctive
What went well? | Improvements? | How?
Communication. The use of Microsoft Teams works well fr our team sprints |  | Keep working!
What issues occurred? | Improvements? | How?
Using GitHub | Need more practice for using GitHub | more experience using it