## User-Stories
ID | Theme | As a/an | I want to | so that | Notes | Priority | Status | Tasks # | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 |  | Product Owner | Store all the customers information | it can be retrieved at any time |  |  |  | 5
[7 empty] | Complete |  | Create Database Model
[7 empty] | Complete |  | Create a relational database
[7 empty] | Complete |  | Validate data input
[7 empty] | Complete |  | Ensure Primary keys are present
[7 empty] | Complete |  | Ensure Foreign keys are present
2 |  | Administrator | Have all data in a relational databse | All related data will be aligned properly |  |  |  | 3
[7 empty] | Complete |  | Enter all customer data
[7 empty] | Complete |  | Enter prescription data
[7 empty] | Complete |  | Enter Doctor Contact information
3 |  | User | A secure login connection | So my order is secured |  |  |  | 3
[7 empty] | Complete |  | Create connection string for form to connect to database
[7 empty] | Complete |  | Create Login page
[7 empty] | Complete |  | Verify username and password
4 |  | User | Use a form for data entry | so it is easier to fill in the required information |  |  |  | 2
[7 empty] | Complete |  | Create Customer Form for data input
[7 empty] | Complete |  | Create textboxes for each data field
5 |  | User | I want access to the database | I can save all data when ordering |  |  |  | 2
[7 empty] | Complete |  | Create save function to insert user data
[7 empty] | Complete |  | Create save button in UI
6 |  | User | Edit my data | I can make changes as needed |  |  |  | 2
[7 empty] | Complete |  | Create edit function to change existing data
[7 empty] | Complete |  | Create edit button in UI
7 |  | User | Log out when finished | my data is secured |  |  |  | 2
[7 empty] | Complete |  | Create Logout Function
[7 empty] | Complete |  | Create logout button in UI
19
8 |  | Administrator | I want all data validated | All data is accurate for orders and reports |  |  |  | 1
[7 empty] | Complete |  | Create validation on Customer form for entering data
|  | Dev Team | Dev Tem | Split validation into two tasks | customer and pharmacist validation are separate |  | Complete |  | Create Validation on Pharmacist form for entering data
9 |  | Pharmacist | Escalated login credentials | I can verify access to higher level functions and data |  |  |  | 3
[7 empty] | Complete |  | Create database role for database Administrator
[7 empty] | Complete |  | Create database role for Pharmacist
[7 empty] | Complete |  | Create database role for Customer
10 |  | Pharmacist | A separate page from customer page | I can access reports and customer list |  |  |  | 3
[7 empty] | Complete |  | Create 3rd panel for Admin UI
[7 empty] | Complete |  | Create reports
[7 empty] | Complete |  | Create Queries
11 | Dev Team | Dev Team | Design changes | Form changes |  |  | Complete | 1 | Change Design Admin Page
12 | Dev Team | Dev Team | Design changes | Form changes |  |  | Complete | 1 | Design Change Dashboard
13 | Dev Team | Dev Team | Design changes | Form changes |  |  | Complete | 1 | Design Change Dashboard
14 | Change Request | Dev Team | Additional Coulmn | Store Username |  |  | Complete | 1 | Add Coulms to Customer Table
15 | Change Request | Dev Team | Additional Coulmn | Drug Refills |  |  | Complete | 1 | Add Coulms to Pharmacy Table
16 | Change Request | Dev Team | Modify Comment Box | To add more Drug Allergies |  |  | Complete |  | Make Allergy Text Box Larger on Form
17 | Change Request | Dev Team | Changes Form Dashboard | Add additional information |  |  | Complete | 1 | Add more data boxes to form
18 | Change Request | Dev Team | Clean up GitHub | Streamline |  |  | Complete | 1 | Clean up Github
16
19 |  | User | View a complete list of my prescritions | so I can select which ones to refill |  |  |  | 2
[7 empty] | Waiting |  | Create autofill of needed data
[7 empty] | Waiting |  | Make a check list for customers to choose from
20 |  | Pharmacist | A full report of the days orders | I know how many prescriptions will be mailed |  |  |  | 2
[7 empty] | Waiting |  | Create reports
[7 empty] | Waiting |  | Create Queries
21 |  | User | Review my order prior to payment | So I can verify it is correct |  |  |  | 1
[7 empty] | Waiting |  | Create Pop-up for order verification
22 |  | User | My mailing address to autofill | So I do not have to enter it every time I order |  |  | Waiting | 1
[7 empty] | Waiting |  | Autofill customers data when logged in
23 |  | Pharmacist | Doctors contact information included | I can request a prescription renewal when needed |  |  |  | 2
[7 empty] | Complete |  | Create a table for primary doctors contact information
[7 empty] | Complete |  | Create Primary/Foreign Keys
24 |  | User | View my order history | I can ensure it is accurate |  |  |  | 1
[7 empty] | Waiting |  | Create a pop up asking user to make sure data is correct before sending order
25 | Dev Team | Dev Team | Functionality update | New user registration |  |  | Complete | 1 | Create new user registration functionality
Create new user checkbox
26 | Dev Team | Dev Team | Security changes | SQL Parameterization |  |  | Complete | 1 | Paramaterize queries
27 | Dev Team | Dev Team | Code cleanup | Organize and label logically |  |  | Complete | 1 | Code cleanup and label organization
9
28 |  | User | A bug free experience | I am sure the application is working correctly |  |  |  | 1
[7 empty] | Waiting |  | Testing
1
[6 empty] | Total Tasks |  | 36

## Product Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2022-02-16 | 36 | 36
Thur | 2022-02-17 | 29 | 33
Fri | 2022-02-18 | 29 | 31
Sat | 2022-02-19 | 29 | 30
Sun | 2022-02-20 | 28 | 26
Mon | 2022-02-21 | 27 | 25
Tues | 2022-02-22 | 26 | 25
Wed | 2022-02-23 | 26 | 24
Thur | 2022-02-24 | 24 | 24
Fri | 2022-02-25 | 21 | 22
Sat | 2022-02-26 | 20 | 20
Sun | 2022-02-27 | 19 | 18
Mon | 2022-02-28 | 18 | 17
Tues | 2022-03-01 | 18 | 16
Wed | 2022-03-02 | 26 | 24
Thur | 2022-03-03 | 25 | 23
Fri | 2022-03-04 | 20 | 18
Sat | 2022-03-05 | 16 | 15
Sun | 2022-03-06 | 15 | 13
Mon | 2022-03-07 | 15 | 13
Tues | 2022-03-08 | 15 | 13
Wed | 2022-03-09 | 15 | 13
Thur | 2022-03-10 | 15 | 13
Fri | 2022-03-11 | 14 | 12
Sat | 2022-03-12 | 12 | 10
Sun | 2022-03-13 | 10 | 8
Mon | 2022-03-14 | 10 | 8
Tues | 2022-03-15 | 10 | 8
Wed | 2022-03-16 | 10
Thur | 2022-03-17 | 10
Fri | 2022-03-18 | 10
Sat | 2022-03-19 | 10
Sun | 2022-03-20 | 9
Mon | 2022-03-21 | 8
Tues | 2022-03-22 | 7
Wed | 2022-03-23 | 6
Thur | 2022-03-24 | 5
Fri | 2022-03-25 | 4
Sat | 2022-03-26 | 3
Sun | 2022-03-27 | 2
Mon | 2022-03-28 | 2
Tues | 2022-03-29 | 2
Wed | 2022-03-30 | 2
Thur | 2022-03-31 | 2
Fri | 2022-04-01 | 1
Sat | 2022-04-02 | 1
Sun | 2022-04-03 | 1
Mon | 2022-04-04 | 1
Tues | 2022-04-05 | 0

## Sprint 1 Planning
User Story | Tasks | Team Member | Hours Estimated | Actual Hours
As a Product Owner I want to store all customer data so it can be retrievd at any time | Create Database Model | Jim | 1 | 2
| Create a relational database | Jim | 6 | 1
| Validate data input | Jim | 1 | 1
| Ensure Primary keys are present | Jim | 1 | 1
| Ensure Forgein keys are present | Jim | 1 | 1
As an Administrator I want to have a ll data in a relational database so all data will be ailigned properly | Enter customer data | Jim | 2 | 3
| Enter prescription data | Jim | 2 | 3
| Enter doctor contact information | Jim | 2 | 3
As a User I want a secure Login connection so my order is secured | Create connection string | Adrian | 1 | 2
| Create Login Page | Sara | 1 | 1
| Verify username and Password | Adrian | 2 | 1
As a User I want a form for data entry so it is easier to fill in my data | Create Customer form for data entry | Sara | 2 | 2
| Create textboxes for each data field | Sara | 1 | 1
As a User, I want to access the database, so that I can save all data when ordering | Create save function to insert user data | Adrian | 1 | 1
| Create save button in UI | Sara | 1 | 1
As a User, I want to edit my data, so I can make changes as needed | Create edit function to update data | Adrian | 1 | 2
| Create edit button in UI | Sara | 1 | 1
As a User, I want to log out when finished so that my data is secured | Create logout function | Adrian | 1 | 1
| Create logout button in UI | Adrian | 1 | 1
|  | Total | 29 | 29
|  | Hours/member | 9.67 | 9.67

## Sprint 1 Burndown
Time |  | Tasks |  |  |  |  | Jim Planned | Jim Daily | Sara Planned | Sara Daily | Adrian Planned | Adrian Daily | Team Planned | Team Daily
Day | Date | Planned | Actual |  |  | Total
Wed | 2022-02-17 | 19 | 19 |  |  | Wed | 8 | 0 | 5 | 0 | 6 | 0 | 19 | 0
Thurs | 2022-02-18 | 19 | 16 |  |  | Thu | 8 | 0 | 5 | 2 | 6 | 1 | 19 | 3
Fri | 2022-02-19 | 16 | 14 |  |  | Fri | 8 | 2 | 3 | 0 | 5 | 0 | 16 | 2
Sat | 2022-02-20 | 14 | 13 |  |  | Sat | 6 | 1 | 3 | 0 | 5 | 0 | 14 | 1
Sun | 2022-02-21 | 13 | 9 |  |  | Sun | 5 | 2 | 3 | 1 | 5 | 1 | 13 | 4
Mon | 2022-02-22 | 9 | 8 |  |  | Mon | 3 | 0 | 2 | 0 | 4 | 1 | 9 | 1
Tues | 2022-02-23 | 8 | 8 |  |  | Tue | 3 | 0 | 2 | 0 | 3 | 0 | 8 | 0
Wed | 2022-02-24 | 8 | 8 |  |  | Wed | 3 | 0 | 2 | 0 | 3 | 0 | 8 | 0
Thurs | 2022-02-25 | 8 | 6 |  |  | Thu | 3 | 0 | 2 | 0 | 3 | 2 | 8 | 2
Fri | 2022-02-26 | 4 | 4 |  |  | Fri | 2 | 1 | 1 | 1 | 1 | 0 | 4 | 2
Sat | 2022-02-27 | 2 | 2 |  |  | Sat | 1 | 1 | 0 | 1 | 1 | 0 | 2 | 2
Sun | 2022-02-28 | 1 | 1 |  |  | Sun | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1
Mon | 2022-03-01 | 1 | 1 |  |  | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Tues | 2022-03-02 | 0 | 0 |  |  | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-Sprint
|  | Planned | Actual | TODO | %
Velocity: |  | 19 | 19 | 0 | 100%
Testing
3 tasks fully tested and passed.
Screenshots
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 1 Demo
Task | By | Accepted | Notes
Create Database Model | Jim | Yes
Create a relational database | Jim | Yes
Validate data input | Jim | Yes
Ensure Primary keys are present | Jim | Yes
Ensure Forgein keys are present | Jim | Yes
Enter customer data | Jim | Yes
Enter prescription data | Jim | Yes
Enter doctor contact information | Jim | Yes
Create connection string | Adrian | Yes
Create Login Page | Sara | Yes
Verify username and Password | Adrian | Yes
Create Customer form for data entry | Sara | Yes
Create textboxes for each data field | Sara | Yes
Create save function to insert user data | Adrian | Yes
Create save button in UI | Sara | Yes
Create edit function to update data | Adrian | Yes
Create edit button in UI | Sara | Yes
Create logout function | Adrian | Yes | Added after mid-sprint
Create logout button in UI | Adrian | Yes | Added after mid-sprint

## Sprint 1 Review
Done | Updated | Notes
2022-03-01 | Product backlog updated for new design concepts | None
| PO satisifed with demo and sprint 1 | None
Changes for next sprint |  |  |  |  | Remarks
1 | The DOB field has the time in it for some reason. I'm not sure if that's a C# issue or a SQL issue, but it looks silly and is causing some problems code-wise. |  |  |  | Changes will be made
2 | We need phone and email textboxes for panel 2 (general user panel). We have them in panel 3, but not 2. |  |  |  | Changes will be made
3 | The extra resources in the repo need to be deleted because they're causing conflicts when I pull from the repo. The form doesn't know which file to use sometimes. They are the form1.cs, form1.designer.cs, and form1.resx and were added when we were figuring out Sara's merge. I have all that in the code now, so no data will be lost |  |  |  | Deleted Screenshot
4 | We have 1 allergy field in the database, but three in the UI. I think we need to decide whether to add more to the database or have just one large text area for the allergy field in the UI |  |  |  | I used one large text field to list allergies. I thought that was easier than multiple
5 | We need to decide for sure how we're going to handle customer lookup. I know it's more work on the db, but I think the easiest option for cleaner code would be to have another column for username in Customers_List. Right now, just to test the code I have it so that I'm looking it up by customer ID, but that could get quite tedious keeping track of which IDs are administrative, etc. |  |  |  | I can add username. I am also thinking of combining name into one bx instead of separate boxes for first and last name. The reason for this is when searching for customer names, you just need to list one column instead of two as it is now
6 | Do you think we need a 4th panel for the customer refill options? Because I'm not quite sure how we're going to handle that at the moment. |  |  |  | can make a 4th panel, will it be easier for you adrian? logically, it could work. Customers would need to input their data first before submitting a refill request.
7 | Sara - if you get bored, you should mess around with the color scheme of the form to set it apart from generic forms. Not terribly important, but it makes it prettier to look at |  |  |  | if only I had the time to be bored xD but yes I will set some time on the side to look into color schemes and such.
End-Sprint
Sprint velocity consisted of 19 tasks assigned and 19 tasks completed. No adjustments needed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 19 | 19
Testing Strategy
All 19 tasks passed testing.
Screenshots
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 1 Retrosepctive
What went well? | Improvements? | How?
Communication. The use of Microsoft Teams works well fr our team sprints |  | Keep working!
What issues occurred? | Improvements? | How?
Using GitHub | Need more practice for using GitHub | more experience using it

## Sprint 2 Planning
User Story | Tasks | Team Member | Hours Estimated | Actual Hours
As an Admin I want all data Validated for accurate | Create Validation on Customer Forms | Adrian | 4 | 4
As A Pharmacist I want Escalated Login credentails so I can have access to higher level functions | Create database role for database Administrator | Jim | 2 | 2
| Create database role for Pharmacist | Jim | 2 | 2
| Create database role for Customer | Jim | 2 | 2
As A Pharmacist I want a separate page from customer page So I can access Reports and customer data | Create 3rd panel for Admin UI | Sara | 4 | 4
| Create reports | Jim | 3 | 5
| Create Queries | Jim | 3 | 4
Dev Team Change Request | Form Design Changes | Sara | 2 | 2
Dev Team Change Request | Form Design Changes | Sara | 2 | 2
Dev Team Change Request | Form Design Changes | Sara | 2 | 2
Dev Team Change Request | Add Coulms to Customer Table | Jim | 1 | 1
Dev Team Change Request | Add Coulms to Pharmacy Table | Jim | 1 | 1
Dev Team Change Request | Make Allergy Text Box Larger on Form | Sara | 2 | 2
Dev Team Change Request | Add more data boxes to form | Sara | 2 | 2
Dev Team Change Request | Clean up Github | Jim | 1 | 1
Dev Team Change Request | Create Validation on Pharmacist Form | Adrian | 3 | 3
|  | Total | 36 | 39
|  | Hours/member | 12 | 13

## Sprint 2 Burndown
Time |  | Tasks | [6 empty] | Jim Planned | Jim Daily | Sara Planned | Sara Daily | Adrian Planned | Adrian Daily | Team Planned | Team Daily
Day | Date | Planned | Actual |  |  |  |  | Total
Wed | 2022-03-02 | 16 | 16 |  |  |  |  | Wed | 8 | 0 | 5 | 0 | 3 | 0 | 16 | 0
Thurs | 2022-03-03 | 16 | 15 |  |  |  |  | Thu | 8 | 0 | 5 | 0 | 3 | 1 | 16 | 1
Fri | 2022-03-04 | 15 | 10 |  |  |  |  | Fri | 8 | 3 | 5 | 2 | 2 | 0 | 15 | 5
Sat | 2022-03-05 | 10 | 7 |  |  |  |  | Sat | 5 | 2 | 3 | 0 | 2 | 1 | 10 | 3
Sun | 2022-03-06 | 7 | 5 |  |  |  |  | Sun | 3 | 0 | 3 | 2 | 1 | 0 | 7 | 2
Mon | 2022-03-07 | 5 | 5 |  |  |  |  | Mon | 3 | 0 | 1 | 0 | 1 | 0 | 5 | 0
Tues | 2022-03-08 | 5 | 5 |  |  |  |  | Tue | 3 | 0 | 1 | 0 | 1 | 0 | 5 | 0
Wed | 2022-03-09 | 5 | 5 |  |  |  |  | Wed | 3 | 0 | 1 | 0 | 1 | 0 | 5 | 0
Thurs | 2022-03-10 | 5 | 5 |  |  |  |  | Thu | 3 | 0 | 1 | 0 | 1 | 0 | 5 | 0
Fri | 2022-03-11 | 5 | 4 |  |  |  |  | Fri | 3 | 0 | 1 | 0 | 1 | 1 | 5 | 1
Sat | 2022-03-12 | 4 | 2 |  |  |  |  | Sat | 3 | 2 | 1 | 0 | 0 | 0 | 4 | 2
Sun | 2022-03-13 | 2 | 2 |  |  |  |  | Sun | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2
Mon | 2022-03-14 | 0 | 0 |  |  |  |  | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tues | 2022-03-15 | 0 | 0 |  |  |  |  | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-Sprint | [5 empty] | Demo Video:
|  | Planned | Actual | TODO | %
Velocity: |  | 16 | 16 | 0 | 100%
Testing
3 test on database completed
3 test on form validation completed
Screenshots
Sprint 2 Demo Video
https://youtu.be/oKUQP-lwgm4
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 2 Demo
Task | By | Accepted | Notes
Create Validation on Customer Forms | Adrian | Yes | Sprint 2 Demo Video:
Create database role for database Administrator | Jim | Yes
Create database role for Pharmacist | Jim | Yes
Create database role for Customer | Jim | Yes
Create 3rd panel for Admin UI | Sara | Yes
Create reports | Jim | Yes
Create Queries | Jim | Yes
Form Design Changes | Sara | Yes
Form Design Changes | Sara | Yes
Form Design Changes | Sara | Yes
Add Coulms to Customer Table | Jim | Yes
Add Coulms to Pharmacy Table | Jim | Yes
Make Allergy Text Box Larger on Form | Sara | Yes
Add more data boxes to form | Sara | Yes
Clean up Github | Jim | Yes
Create Validation on Pharmacist Form | Adrian | Yes

## Sprint 2 Review
Done | Updated | Notes
2022-03-14 | All Good
Changes Requested
Panel 2, 4, 5
-Change payment method to Credit Card Number
-add expiration date
panel 1
-add checkbox for new user
End-Sprint
Sprint velocity consisted of 16 tasks assigned and 16 tasks completed. No adjustments needed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 16 | 16
Testing Strategy
All 16 tasks passed testing.
Screenshots
See Demo Video in Demo Tab
Code
https://github.com/JimSoy/SM-Consultants

## Sprint 2 Retrospective
What went well? | Improvements? | How?
Communications are going great | None
What issues occurred? | Improvements? | How?
GitHub still posses a few challenges | Experience is the best teacher. | More time using it

## Sprint 3 Planning
User Story | Tasks | Team Member | Hours Estimated | Actual Hours
As a user, I want to see a complete list of my medications so I can select the ones I need refilled | Create autofill of needed data | Adrian | 1
| Make a check list for customers to choose from | sara | 2 | 2
As a pharmacist, I want to see a report showing all the orders for the day | Create a report of the days prescriptions
Create a query to search for any needed refills
| create designated area for reporting, query by date range, order status, daily fill queue. | sara | 1 | 1
As a user, I need to review my order before submittingit so I can be sure it is correct | Create Pop-up for order verification | Adrian | 2
As a user, I would like my data like address and payment information to auto-fill the form, so I do not have to re-type my information every time. | Autofill customers data when logged in | Adrian | 2
As a Pharmacist, I want easy access to all doctor information, so I can reach out to renew a presripction for more refills | Create a table for primary doctors contact information | Jim | 2 | 2
| Create Primary/Foreign Keys | Jim | 1 | 1
| Create a form for displaying Doctor Info | sara | 1 | 1
As a user, I want to make sure my information is correct before I submit it when I register, so it is accurate | Create a pop up when submit is pressed, to confirm information before submitting | Adrian | 1
Dev Team Request | Design UI with aesthetics | sara | 2 | 2
Dev Team Request | Add order History table | Jim | 2
Dev Team Request | Add new user functionality | Adrian | 2 | 2
Dev Team Request | Add new user checkbox | Sara | 1 | 1
Dev Team Request | Parameterize SQL queries | Adrian | 2 | 2
Dev Team Request | Code cleanup and label organization | Adrian | 4 | 4
|  | Total | 26 | 18
|  | Hours/member | 8.6667 | 6

## Sprint 3 Burndown
Time |  | Tasks | [6 empty] | Jim Planned | Jim Daily | Sara Planned | Sara Daily | Adrian Planned | Adrian Daily | Team Planned | Team Daily
Day | Date | Planned | Actual |  |  |  |  | Total
Wed | 2022-03-16 | 14 | 11 |  |  |  |  | Wed | 3 | 0 | 4 | 0 | 7 | 3 | 14 | 3
Thurs | 2022-03-17 | 11 | 11 |  |  |  |  | Thu | 3 | 0 | 4 | 0 | 4 | 0 | 11 | 0
Fri | 2022-03-18 | 11 | 10 |  |  |  |  | Fri | 3 | 0 | 4 | 1 | 4 | 0 | 11 | 1
Sat | 2022-03-19 | 10 | 8 |  |  |  |  | Sat | 3 | 2 | 3 | 0 | 4 | 0 | 10 | 2
Sun | 2022-03-20 | 7 | 6 |  |  |  |  | Sun | 1 | 0 | 2 | 2 | 4 | 0 | 7 | 2
Mon | 2022-03-21 | 6 | 6 |  |  |  |  | Mon | 1 | 0 | 1 | 0 | 4 | 0 | 6 | 0
Tues | 2022-03-22 | 6 | 6 |  |  |  |  | Tue | 1 | 0 | 1 | 0 | 4 | 0 | 6 | 0
Wed | 2022-03-23 | 0 | [5 empty] | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thurs | 2022-03-24 | 0 | [5 empty] | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fri | 2022-03-25 | 0 | [5 empty] | Fri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sat | 2022-03-26 | 0 | [5 empty] | Sat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sun | 2022-03-27 | 0 | [5 empty] | Sun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mon | 2022-03-28 | 0 | [5 empty] | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tues | 2022-03-29 | 0 | [5 empty] | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-Sprint | [6 empty] | Demo Video:
|  | Planned | Actual | TODO | %
Velocity: |  | 17 | 8 | 9 | 47.06% | Remaining 6 to be finished by end of sprint
Testing
3 test on database completed
3 test on form validation completed
Screenshots
Code
https://github.com/JimSoy/SM-Consultants